## Task Breakdown
STORY NAME | TASK NUMBER | TASK DESCRIPTION | STATUS | ESTIMATED EFFORT(weeks) | Effort Remaining | Sprint Days
Automated testing, CI and CD environment setup, sprint back log | 0.1 | Sprint Back-log | Open | 3 | 3 | 2015-06-22
| 0.2 | CI & CD Setup | Open | 3 | 3 | 2015-06-22
| 0.3 | Automated Testing setup | Open | 3 | 3 | 2015-06-22
STORY NAME | TASK NUMBER | TASK DESCRIPTION | STATUS | ESTIMATED EFFORT(weeks) | Effort Remaining | Sprint Days | Ideal Effort
GROUP CHAT | 1 | Create Chat | Open | 2 | 2 | 2015-07-05 | 900
| 2 | Delete Chat | Open | 1 | 1 | 2015-07-12 | 800
| 3 | Add and delete users | Open | 1 | 1 | 2015-07-19 | 700
| 4 | Members Receive Mgs | Open | 2 | 2 | 2015-08-02 | 600
| 5 | Secure Group Chat | Open | 2 | 2 | 2015-08-16 | 500
INTERFACES | 6 | Group Chat Interface | Open | 3 | 3 | 2015-09-06 | 400
| 7 | Change Message Interface | Open | 1 | 1 | 2015-09-13 | 300
RECORDING | 8 | Voice Recoding | Open | 2 | 2 | 2015-09-27 | 200
| 9 | Send Recording | Open | 1 | 1 | 2015-10-04 | 100
Demo | 10 | Testing the system to ensure that no bugs and errors are found | Open | 2 | 2 | 2015-10-23 | 0
s
Burn-Down Chart
Remaining Effort
Sprint Dates

## User Role
USER STORY | TASKS | ASSIGNED TO
I can create a group chat and add at least 1 member, I can select members from my contact list to be apart of the group chat. | Code the create chat function | Ephiphania
| Code the add user function | Lerato
| Design UI | Tsepo
| Unit Test | Lutifiyya
| Automated Test(CI & CD) | Patience
After the group chat is completed I can (as the administrator) delete the chat, At anytime I can remove a member from the group chat | Code the delete chat function | Potego
| Delete Users | Ephiphania
| Unit Test | Lerato
| Automated Test(CI & CD) | Lutifiyya
In the group chat one member sends a message in the group all the other members will receive it | Code send messages to members | Patience
| Code receive messages to members | Potego
| Design UI | Tsepo
| Unit Test | Ephiphania
| Automated Test(CI & CD) | Lerato
The group chats have to be secure. | Secure Group Chat | **Research
As a user I should be able to send and receive voice recordings | Send voice recording | Lutifiyya
| Receive voice recoding | Patience
| Voice Recoding | Potego
| Design UI | Tsepo
| Unit Test | Ephiphania
| Automated Test(CI & CD) | Lerato
The message interface should appeal to me as the user | Space between words | Lutifiyya
| Font modification | Patience
| Indents blocks | Potego
| User presence | Tsepo
| User picture | Ephiphania
Testing | Testing the system to ensure that no bugs and errors are found | *Baobab